## Sheet1
Code Review 2 | Criteria | Result | Assigned to
Fit for Purpose | Website is hosted on web host | Website is hosted on GoDaddy
| Accessible over the internet | Website is accessible
| Wordpress is installed on web host | Wordpress is installed
| Login available for group members in order to work on project | Login is available through WP-admin
| Game is relevant to the driver’s test and can accommodate question/answers | Game is relevant, needs to prompt MVA questions | Max
| Upload Game to web host | Game is uploaded to Wordpress
Code Duplication/Integrity | No conflicts between plugins and Wordpress | Plugin may cause login problems, currently no issue
| Single instance of pages and content | Need home page for website | Kenny
| Github repository is connected through cPanel Admin | Github is connected
| Files in their proper folder in the file system | Files are viewable and found in proper folders
Style/Readability | HTML/CSS/Javascript code on Wordpress pages are properly formatted | Code is properly formatted, plugins were used
| Comments are used to indicate function of any code embedded on pages | No comments were needed
| Install Wordpress theme and ensure no conflict with other features | Theme is installed and layout was made
Website User login | Login page skeleton for User, Parents, MVA | Login page is available
| Appropriate fields available for registration | Registration fields are still needed | Ola
| Password reset link available | Password link is available
| Incorporate Social Media Login (Facebook) | Social media login isn't available | Ola/Caitlin
Documentation | Documentation updated and reflects actual product | Test Skeleton needs to be updated | Angina
|  | Class diagram/interface needs to be updated | Krysta